## Sheet1
UpStage semester 2 2014 Project Plan
Version: |  |  | 1.0 |  | Prepared By: | Takuma & Yue
| Blog Post | Version 3 maintenance (Pair programming) | Allocated Pair | Research topics / Work schedule | Action / Deliverable | Number of Researcher(s)
Week 1
Week 2
Week 3
Week 4 | Yes
Week 5
Week 6 | Yes | #225 - Save stage reminder | Takuma Gaoxin | Replacement for Flash Plugin | Define the feature of Flash plugin | 3
|  | #207 - built-in invisible avatar option | James Charlotte | Text2speech technologies | Complete report on available technology | 1
|  | #200 - Delete player no warning | XiangYu Yue | Video streaming technology | Analyse the role and functions of VideoHack in UpStage | 2
Break |  | #225 - Save stage reminder | Takuma Gaoxin | Replacement for Flash Plugin | Start looking for technologies to replace Flash | 3
|  | #207 - built-in invisible avatar option | James Charlotte | Text2speech technologies | Provide small program as a proof of concept and evaluate | 1
|  | #200 - Delete player no warning | XiangYu Yue | Video streaming technology | Produce a report on feasible video stream technology | 2
Break | Yes | #207 - built-in invisible avatar option | James Charlotte | Replacement for Flash Plugin | Provide proof of concepts | 3
|  | #199 - Renaming avator with right click menu | TBA
|  | #198 - Audience applause sound | TBA | Video streaming technology | Continue research on video stream technology | 3
Week 7 |  | #199 - Renaming avator with right click menu | TBA | Research testing framework | Look into different languages and evaluate | 2
|  | #198 - Audience applause sound | TBA | Replacement for Flash Plugin | Evaluation of prototype | 2
|  | #87 - Making chat opening message editable | TBA | Video streaming technology | Attemp to create a small program or document to proof how it maybe done | 2
Week 8 | Yes | #198 - Audience applause sound | TBA | Research testing framework | Look into IDEs that supports various testings and evaluate | 3
|  | #195 - Right click menue "fast/slow" does not update | TBA | Find suitable database for the project | Produce report on whether to continue to use existing one or to replace | 3
|  | #231,219,216 - Sort media display | TBA
Week 9 |  | #231,219,216 - Sort media display | TBA | Research testing Framwork | Produce a recommendation (metrics) for each language and IDEs | 2
|  | #151 - Font resizing buttons | TBA | View Stage as audience from mobile device | Find technology to enable user to access UpStage from mobile devices | 4
|  | #195 - Right click menue "fast/slow" does not update | TBA
Week 10 | Yes | #231,219,216 - Sort media display | TBA | Research testing Framwork | Select languages that would enable us to have | 2
|  | #151 - Font resizing buttons | TBA | View Stage as audience from mobile devices | Find technology to enable user to access UpStage from mobile devices | 4
|  | #210 - Rotate avatar, or flip | TBA
Week 11 |  |  | TBA | Research compatibility between each technology | Prepare a matrix for matching the technologies | 2
Week 12 | Yes |  | TBA | Prepare Development Strategy for different technologies | A document explains the importance of the technologies and how to resolve conflicts between different technologies during software development | 3