## Sheet1
| Blog post | Version 3 maintenance (Pair programming) | Allocated Pair | Research topics | Action / Deliverable | number of Researcher
Week 1
Week 2
Week 3
Week 4 | Yes
Week 5
Week 6 | Yes | #225 - Save stage reminder | Takuma, Gaoxin | Replacement for Flash Plugin | Define the feature of Flash plugin
|  | #207 - built-in invisible avatar option | James, Charlotte | Text2speech technologies | Find available technology
|  | #200 - Delete player no warning | XiangYu, Yue | Video streaming technology | Analyse the role and functions of VideoHack in UpStage
Week 7 |  | #225 - Save stage reminder | Takuma, Gaoxin | Replacement for Flash Plugin | Start looking for technologies to replace Flash
|  | #207 - built-in invisible avatar option | James, Charlotte | Text2speech technologies | Find available technology
|  | #200 - Delete player no warning | XiangYu, Yue | Video streaming technology | Produce a report on feasible video stream technology
Break | Yes | #207 - built-in invisible avatar option | Takuma, Gaoxin | Replacement for Flash Plugin | Start looking for technologies to replace Flash
|  | #199 - Renaming avator with right click menu | James, Charlotte | Text2speech technologies | Find available technology
|  | #198 - Audience applause sound | XiangYu, Yue | Video streaming technology | Produce a report on feasible video stream technology
Break |  | #199 - Renaming avator with right click menu | Takuma, Gaoxin | Replacement for Flash Plugin | Start looking for technologies to replace Flash
|  | #198 - Audience applause sound | James, Charlotte | Text2speech technologies | Find available technology
|  | #87 - Making chat opening message editable | XiangYu, Yue | Video streaming technology | Produce a report on feasible video stream technology
Week 8 | Yes | #198 - Audience applause sound | Takuma, Gaoxin | Replacement for Flash Plugin | Start looking for technologies to replace Flash
|  | #195 - Right click menue "fast/slow" does not update | James, Charlotte | Text2speech technologies | Find available technology
|  | #231,219,216 - Sort media display | XiangYu, Yue | Video streaming technology | Produce a report on feasible video stream technology
Week 9 |  | #231,219,216 - Sort media display | Takuma, Gaoxin | Replacement for Flash Plugin | Start looking for technologies to replace Flash
|  | #151 - Font resizing buttons | James, Charlotte | Text2speech technologies | Choosing suitable technology
|  | #195 - Right click menue "fast/slow" does not update | XiangYu, Yue | Video streaming technology | Select a feasible video stream technology
Week 10 | Yes | #231,219,216 - Sort media display | Takuma, Gaoxin | Replacement for Flash Plugin | Start looking for technologies to replace Flash
|  | #151 - Font resizing buttons | James, Charlotte | Text2speech technologies | Choosing suitable technology
|  | #210 - Rotate avatar, or flip | XiangYu, Yue | Video streaming technology | Select a feasible video stream technology
Week 11
Week 12 | Yes