## Sheet1
| Blog post | Version 3 maintenance (Pair programming) | Allocated Pair | Research topics | Action / Deliverable | number of Researcher
Week 1
Week 2
Week 3
Week 4 | Yes
Week 5
Week 6 | Yes | #225 - Save stage reminder | Takuma, Gaoxin | Replacement for Flash Plugin | Define the feature of Flash plugin
|  | #207 - built-in invisible avatar option | James, Charlotte | Text2speech technologies | Find available technology
|  | #200 - Delete player no warning | XiangYu, Yue | Video streaming technology | Analyse the role and functions of VideoHack in UpStage
Week 7 |  | #225 - Save stage reminder | Takuma, Gaoxin | Replacement for Flash Plugin | Start looking for technologies to replace Flash
|  | #207 - built-in invisible avatar option | James, Charlotte | Text2speech technologies | Find available technology
|  | #200 - Delete player no warning | XiangYu, Yue | Video streaming technology | Produce a report on feasible video stream technology
Break | Yes | #207 - built-in invisible avatar option | Takuma, Gaoxin | Replacement for Flash Plugin | Start looking for technologies to replace Flash
|  | #199 - Renaming avator with right click menu | James, Charlotte | Text2speech technologies | Find available technology
|  | #198 - Audience applause sound | XiangYu, Yue | Video streaming technology | Produce a report on feasible video stream technology
Break |  | #199 - Renaming avator with right click menu | Takuma, Gaoxin | Replacement for Flash Plugin | Start looking for technologies to replace Flash
|  | #198 - Audience applause sound | James, Charlotte | Text2speech technologies | Find available technology
|  | #87 - Making chat opening message editable | XiangYu, Yue | Video streaming technology | Produce a report on feasible video stream technology
Week 8 | Yes | #198 - Audience applause sound | Takuma, Gaoxin | Replacement for Flash Plugin | Start looking for technologies to replace Flash
|  | #195 - Right click menue "fast/slow" does not update | James, Charlotte | Text2speech technologies | Find available technology
|  | #231,219,216 - Sort media display | XiangYu, Yue | Video streaming technology | Produce a report on feasible video stream technology
Week 9 |  | #231,219,216 - Sort media display | Takuma, Gaoxin | Replacement for Flash Plugin | Start looking for technologies to replace Flash
|  | #151 - Font resizing buttons | James, Charlotte | Text2speech technologies | Choosing suitable technology
|  | #195 - Right click menue "fast/slow" does not update | XiangYu, Yue | Video streaming technology | Select a feasible video stream technology
Week 10 | Yes | #231,219,216 - Sort media display | Takuma, Gaoxin | Replacement for Flash Plugin | Start looking for technologies to replace Flash
|  | #151 - Font resizing buttons | James, Charlotte | Text2speech technologies | Choosing suitable technology
|  | #210 - Rotate avatar, or flip | XiangYu, Yue | Video streaming technology | Select a feasible video stream technology
Week 11 |  |  | Takuma, Gaoxin | Replacement for Flash Plugin | Create proof of concept for a replacement of flash
|  |  | James, Charlotte | Text2speech technologies | Create proof of concept for text to speech without flash
|  | #195 - Right click menue "fast/slow" does not update | XiangYu, Yue | Video streaming technology | Create proof of concept for video streaming technology replacement
Week 12 | Yes | Finishing members to draft Poster and send to Anne by | Takuma, Gaoxin | Replacement for Flash Plugin | Finish proof of concept for a replacement of flash
|  | the end of the week | James, Charlotte | Text2speech technologies | Finish proof of concept for text to speech without flash
|  | James, Xiangyu, Takuma | XiangYu, Yue | Video streaming technology | Finish proof of concept for video streaming technology replacement
Week 13 |  | Changes to Poster for presentation in week 14 | James, Xiangyu, Takuma |  | Poster, Portfolio, Reflective Reports
|  | #? | Gaoxin, Charlotte, Yue | Current UpStage Research | Team Development Manual, Project Plan, Proofs of Concepts for Clients
|  | End of week Regression Test | All |  | Updated Acceptance Test Sheet
Week 14 | Yes | #? | Gaoxin, Charlotte, Yue | Plan work for break and next semester | Team Development Manual, Project Plan, Proofs of Concepts for Clients
|  | Thursday 6th November - Poster Presentation | James, Xiangyu, Takuma |  | Poster, Portfolio, Reflective Reports
Self Reflective Reports Due
Final Portfolio Due